# TENDER NO. PUR: 51934 dated 12.04.25

Tender for Integrated work for establishment of Distribution Substation (33/11-6 kV voltage level) at CESC Limited, Kolkata

CESC Limited (CESC), a power utility in private sector and a flagship company under RP-Sanjiv Goenka Group, is engaged in generation and distribution of electricity in and around Kolkata & Howrah to a consumer base of 34 lakh spread over an area of 567 sq km.

CESC plans to construct Two (2) nos. 33/11-6 kV Distribution Station (D/S) as follows:

Part A: Mukundapur D/S under this tender on EPC basis at near to Avidipta Housing Complex, Premises no – 401, Barakhola , Mukundapur, Kolkata-700099

Part B: Barisha East D/S under this tender on EPC basis at Aagaman Housing Complex developed by Rajat group at 591A, Motilal Gupta Road. Kolkata – 700008

CESC invites Bids in following two parts from Bidders within the deadline mentioned in the clause #2 below:

- Unpriced Technical Bid

- Price Bid with commercial terms & conditions

- Scope of Work:

Package 1: Scope of work as mentioned under Section I (Part A) excluding Supply of Power Transformer, RMU and AIS Pannel.

Package 2: Scope of work as mentioned under Section I (Part B) excluding Supply of Power Transformer, RMU and AIS Pannel.

Detailed Scope of Work as well as other technical details have been furnished, as attached.

- Submission of Bid:

- The last date and time of submission of the Bid Document is 10th May, 2025 (up to 6.00 p.m.).

- Bids shall not be accepted after the deadline date and time.

- No alteration in the form of the Bid or in the amount or any addition in the form of special stipulation will be permitted. If corrections be needed while filling in the Bid, the same shall be made by the Bidder with his dated signature.

- All pages of the Bid papers and other accompanying documents shall be initialled at the lower right-hand corner with ink only and signed where required by the Bidder or any person holding Power of Attorney authorizing him to sign on behalf of the Bidder before submission of the Bid.

- Bid, which is incomplete, obscure or irregular or only for a part of the schedule, is liable for rejection.

- Technical Bid shall be submitted over email (marking chandra.sahoo@rpsg.in, copy to ushnish.basu@rpsg.in)

  - Technical Bid:

- Technical Bids to be submitted in two separate files for individual Distribution Station & the file name should be as below:

- Mukundpur DS - Technical Bid - Bidder Name

- Barisha East DS - Technical Bid - Bidder Name

- Each Technical Bid should consist of following documents:

- Detailed project plan (Gantt Chart & Details) mentioning the following aspect of project:

- Complete scope of Work including material deliveries & service activities

- Completion & HOTO – Feb ‘26.

- Signed copy of Scope of Work & Specifications.

- Acceptance of tender Terms & Conditions (On Company letter head duly signed by authorized signatory)

- No deviation (Annexure – XX On Company letter head duly signed by authorized signatory)

- Submission of GTP (Guaranteed Technical Parameters) / Drawing / other technical documents of all major equipment’s from respective OEMs as recommended by CESC in the Scope of work document.

- Unpriced detailed BOM for the entire projects.

  - Price Bid:

- Price bid to be sent through password protected PDF / Excel File over email to ushnish.basu@rpsg.in Password to be submitted on request from CESC Limited and emailed to  tender.cesc@rpsg.in

- Price Bids to be submitted in two separate files for individual Distribution Station as the format mentioned in the tender document – (Annexure-I/ Scheduled of Item) & the file name should be as below:

- Mukundpur DS - Price Bid - Bidder Name

- Barisha East DS - Price Bid - Bidder Name

- EMD:

The bidders are required to furnish a Demand Draft of INR 5 Lakh (INR Five Lakh only) from any scheduled bank as EMD, which is to be submitted at the address mentioned below.

EMD shall be forfeited if bidder declined to accept the Work Order at his quoted/agreed rates and /or fails to start/execute the job after getting the Order.

EMD shall be converted to interest free Security Deposit for the successful bidder to whom Work Order is issued. The same shall be released after successful commissioning & handing over of the Distribution Station.

BIDS WITHOUT EMD WILL NOT BE ACCEPTED.

Contact Person:

All correspondence/ inquiry with respect to above may be directed to:

Name: Mr. Chandra Sekhar Sahoo

Contact No: 7894441407

E-Mail ID: chandra.sahoo@rpsg.in

Senior Manager – Materials

Name: Mr. Ushnish Basu

Contact No: 9831420495

E-Mail ID: ushnish.basu@rpsg.in

DGM – Materials

Name: Mr. Umesh Bharadwaj

Contact No: 9871552975

E-Mail ID: umesh.bhardwaj@rpsg.in

- Validity of Bid:

Offer shall be valid for at least 90 (ninety) days from the date of submission

- Instruction to Bidders:

  - Owner may at his discretion, extend deadline for submission.

  - Bidders are advised to study the bid document carefully. Submission of bids against the tender notice shall be deemed to have been done after careful study and examination of the procedure, terms and conditions stipulated in the bid documents with full understanding of its implications.

  - The Owner reserves the right to cancel any or all the bids without assigning any reason thereof.

  - No deviation from the Technical Specification & Technical Conditions shall be acceptable unless permitted in writing by the Owner.

  - Before Submission of the Bid, the Bidder is advised to fully familiarize himself with the site conditions, road connectivity, logistic aspects etc. The land for Distribution Station shall be made available to the Bidder on 'as is where is' basis. Further levelling and development of the land shall be in the Bidder's scope of work. It shall be the responsibility of the Bidder to arrange all inputs required for detailed engineering, design and execution. Bidders are, therefore, advised to visit the Distribution Station site, collect all necessary inputs and acquaint themselves with the topography, infrastructure etc. It shall be deemed that the Bidders have thus acquainted themselves with the site conditions.

  - Bidders shall be fully responsible for providing all equipment, materials, system and services specified or otherwise which are required to complete the construction, successful testing and commissioning of the Works. Bidders are required to make themselves fully conversant with the technical specifications, drawings, Special Conditions of specification, Instruction to Bidder, General Technical requirement of specification, Specification for handling, erection, testing & commissioning including schedules as may be applicable so that no ambiguity arises at a later date in this respect.

  - The Bid shall be prepared and submitted strictly in accordance with the instruction contained in these specifications and shall be complete in all respects. The interpolations, insertion, striking out and corrections made in the Bid offers should be duly initialled by the Bidder.

  - Bidders shall duly fill up all schedules enclosed with the bid and supply the data (e.g. GTP, Technical Data etc. which shall be compared with other bidder’s offer) also in XLSX format against each item.

  - In case the Bidder does not supply any of the required information at the time of Bid, necessary loading may be made by the Owner at its sole discretion while evaluating the prices of his offer without giving any further opportunity to supply or clarify the same. The Bidders are notified that in case the required information is not furnished in the specified proforma/schedules attached with the specification, the Owner shall not be responsible for any error in the evaluation of their Bids on this account. Further, failure to comply with this requirement may result in the rejection of the Bid at the discretion of the Owner.

  - A set of technical, descriptive and illustrative literature along with drawings must accompany each copy of the Bid so that a clear understanding of the equipment offered is obtained.

  - CESC reserves the right to split the order package-wise or sub-package wise depending on the need to one or multiple bidders at CESC’s sole discretion.

- Price Basis:

Bidders are requested to provide total price along with the break-up detailing unit rates and quantities.

All Unit rates and amounts to be quoted shall be firm, including all taxes and duties, except GST. No other charges shall be payable extra beyond the above quoted rate.

In case of any statutory variation in the existing GST which is clearly indicated in price break up will only be taken into account with proper documentary evidence. However, any increase in existing GST rate, if applicable due to delay for reasons attributable to Vendor, shall have to be borne by Vendor.

- Terms of Payment:

The payment shall be released within 60 days from the date of receipt of certified and error-free invoice along with the supporting documents based on following milestone basis.

| Stage | Milestone Description | % of Contract Value | Supporting Documents for Payment |
| --- | --- | --- | --- |
| 1 | LOI/PO acceptance, submission of PG, design kickoff | 5% (Advance) | BG for advance, PG, Design kick-off letter |
| 2 | Approval of drawings, civil layout, mobilization at site | 10% | Approved drawings, mobilization photos/report |
| 3 | Completion of civil works upto plinth & Building | 15% | Site verification, civil QC report |
| 4 | Completion of equipment erection | 15% | Site erection report, photos, checklists |
| 5 | Testing & pre-commissioning of panels, SCADA, cabling | 15% | Test Reports, relay config file, SCD file |
| 6 | Completion of all civil finishing, drain, roads, firefighting system | 15% | Site report, HOTO checklist partial |
| 7 | Final commissioning and energization | 15% | Commissioning certificate from CESC |
| 8 | HOTO, submission of final as-built drawings & documents | 10% | HOTO certificate, O&M manuals, as-built sets and submission of PBG of 10% of the contract value and valid for the defect liability period as mentioned in Clause No.11 |

- Time of Completion:

The Distribution Station shall be completely supplied, erected, installed, tested and commissioned by 28th February,2026. The project shall be monitored as per approved project implementation schedule.

- Bidder should submit:

- A detailed project plan (Gantt Chart & Details) mentioning the following aspect of project:

- Complete scope of Work including material deliveries & service activities

- Completion & HOTO – Feb ‘26.

- A list of plant & equipment available with the Contractor along with details of manpower shall also be furnished.

- Liquidated Damages:

  - Time is Essence of the Contract

  - Contractor shall complete the entire Works covered under the Contract within time period specified as above (Clause No. 8) and any delay in completion will attract Liquidated Damages (LD) as per LD Clause mentioned below.

  - Contractor guarantees to complete all supply, construction, erection and commissioning and related activities by the agreed completion date (28th February,2026).

  - In the event of failure by Contractor to meet the agreed completion date, Contractor shall pay to Owner, as Liquidated Damages a sum of 1(one)% of the Contract Price for per week of delay or part thereof subject to ceiling of 10 (ten) % of the Contract price.

  - The Owner reserves the right to deduct any applicable liquidated damages from payment due to the contractor.

  - Payment or deduction of Liquidated Damages shall in no way relieve the Contractor from completing the Works and discharging it’s all other obligations under the Contract

  - It is further agreed this Clause shall not constitute a waiver of any rights of Owner to damages and / or other remedies of Owner under the Contract or otherwise for Contractor’s improper performance or default in performance of any other aspect of the Contract.

- Mobilization of Equipment:

The Contractor should mobilize fully within 15 days from the date of placement of work order or written instructions given. Mobilization shall include but not limited to the followings:

  - All required tools and tackles, welding machines, cutting sets, Chain Blocks, Extension Plug Board, etc.

  - Hydra, Cranes and all sorts of loading / unloading and material handling equipment.

  - All construction, earthmoving equipment including materials related to civil work.

  - All tools and tackles (Mechanical & Electrical) should have proper identification marks and valid certificates, wherever applicable. CESC reserves the right to check (re-test thru certified part/s – the charges have to be borne by vendors) or reject any such tools and tackles, if found unsafe.

  - Contractor shall make adequate arrangements of mechanized material lifting and handling tools (such as, hydra, chain blocks, slings, D-shackles etc.) and should ensure continuous and round the clock availability in healthy condition of these equipment to avoid any disruption/difficulty in work.

- Defect Liability Period:

Defect Liability Period shall mean the period during which the Contractor shall remain liable for repair or replacement of any defective portion of the Works performed under the Contract to the satisfaction of the Owner. Such period shall commence from commissioning & handover of the Distribution Station and continue for a period of 24 months thereafter. Defects reported within the defect liability period shall be addressed within 24 hours of reporting the incidents.

- Latent Defect:

A Latent Defect is a defect that is not capable of being detected by ordinary inspection, but lies hidden until sometime later, when it is discovered because it affects the operation of the Works that is visible or otherwise easily discernible. An example would be weak concrete in part of a bridge column, that looks the same as strong concrete, but collapses when a heavy truck drives over the bridge. It is clarified that such an example is only illustrative and not exhaustive of the possible Latent Defects.

The Contractor is responsible for any latent defects discovered during the first 5 years from the date of expiry of Defect Liability Period.

- Warranty:

The equipment supplied as per scope shall be new, in good condition, conform to the specifications as per relevant national and international standards and shall be free from defects, bad workmanship and faulty design.

The Contractor shall arrange warranty from the respective OEMs for trouble free operation of the equipment for a period of 60 (sixty) months from the date of commissioning of the equipment or 66 (sixty-six) months from the date of delivery of the equipment to site, as directed in the dispatch instruction, whichever is later. Normally, Warranty period shall be reckoned to have started from the date of delivery. However, in the case of short supplies in the consignment, warranty period shall start from the date of completion of such delivery to the full satisfaction of the Owner.  It shall be the Contractor’s responsibility to replenish the short-supplied equipment within 30 (Thirty) days from the date of reporting such short supplies.

In the event of any defective item detected during the warranty period, it shall be the Contractor’s responsibility to arrange replacement of the said equipment within 30 (Thirty) days from the date of reporting such defects.

Such replaced equipment shall be warranted for a period of 60 (sixty) months from the date of installation at site.

In the event, defective workmanship viz. Wiring, labelling, ferruling etc. are detected at site, it shall be the Contractor’s responsibility to arrange for rectification within 15 (Fifteen) days from the date when such defects are detected and notified.

In the event of emergency or when the OEM fails to take remedial actions within reasonable time and where in the Owner’s judgement, delay would cause serious loss or damage, replacement/repairs/adjustments may be made by the Owner or any third party appointed by the Owner without advance notice to the Contractor and the cost of such replacement/repairs/adjustments work shall be borne by the Contractor or its chosen OEM. In the event such action is taken by the Owner, the Contractor shall be notified promptly and the Contractor shall assist, wherever possible, in making the replacement/repairs/adjustments. This shall not relieve the Contractor of any of its liabilities under terms and conditions of the contract.

In the event of any defect attributable to defective component, bad workmanship or faulty design being detected during the warranty period, the Owner shall have the option of verifying it in a third-party laboratory at the Contractor’s cost. However, this will not relieve the Contractor of the responsibility to replace/renew such defective items within the time stipulated as per milestones. The third-party report shall be binding on the Contractor and any defects attributable to the Contractor shall have to be rectified at the total cost (materials and labour) by the Contractor within a mutually agreed upon time frame.

- Insurance Requirements:

The contractor shall take and maintain the following insurance policies at their own cost:

  - Transit Insurance: Covering all equipment from manufacturer/vendor premises to project site.

  - Erection All Risk (EAR) Insurance: Covering the entire site from the date of first delivery till successful commissioning (including free issue material by CESC).

  - Storage Insurance: For all equipment/materials stored at the site warehouse or open yard.

  - Third-Party Liability Insurance: Covering injuries to third-party workers and damages to adjacent properties.

  - Workmen Compensation Insurance: As per statutory requirements.

All policies must name the employer as co-insured and be submitted before the first dispatch.

- Performance Bank Guarantee:

  - Bidder shall furnish Performance Bank Guarantee covering 10% of the Work Order value and which shall remain valid up to 2 (two) years from the date of commissioning.

  - In the event there is a delay in submission of Performance Bank Guarantee, the Owner shall have the right to withhold payment against Invoices at its discretion till such Bank Guarantee is furnished as per requirement.

  - The format of Performance Bank Guarantee shall be provided by the Owner.

  - The Performance Bank Guarantee shall be released and returned after expiry of the Defect Liability Period and after full realization by the Owner of all recoverable amounts (if any) due from the Bidder in terms of the contract. Bidder shall be liable to pay to the Owner such recoverable amounts or the same shall be deducted by the Owner from the Bidder’s bill(s) before release and return of the Performance Bank Guarantee to the Bidder.

- Local Issues:

Contractor should maintain good rapport with the local people during the work, so that the job can be completed smoothly. All the incidental expenses on account of any local issues are to be borne by the Contractor.

- Special Conditions of the Contract (SCC): As per Section III

- General Condition of Contract (GCC): As per Section II

- Safety Terms & Condition: As per Section IV

- Stoppage of Work:

If at any time the Owner decides to abandon or reduce the scope of work for any reason whatsoever the payment shall be made according to the reduced scope of work and the contractor shall not be eligible for any claim regarding payment of compensation.

- General:

- CESC shall not be responsible for misplacement or late receipt of Bid Documents.

- Bid Documents are not transferable

- CESC reserves the right to reject the proposal of any or all Bidders’ without assigning any reasons whatsoever.

- CESC reserves the right to exclude and/or include any line item at later stages as per the requirement for completion and timely execution of the project. Hence bidders are requested to quote their best rate in each line item.

- CESC reserves the right to conduct the reverse auction and/or negotiation for the products/ services being asked for in the tender.

- CESC reserves right to award the contract to the technically qualified bidder whose bid has been determined to be the lowest on overall BoQ basis (Lot wise).

- Bidder shall adhere the OEM/Manufactures of individual equipment specified by CESC. Deviation may lead to disqualification unless specifically approved by CESC authorized personnel.

- CESC reserves the right to cancel or withdraw the bidding process at any time during the process without assigning any reasons and shall bear no liability consequent upon such a decision.

- CESC reserves the right to split the job to multiple Bidders for best techno-commercial benefit & delivery/completion schedule.

- In the event of any ambiguity / conflict / discrepancy / inconsistency / repugnance in any clause amongst Tender, Scope of Work, SCC & GCC; the said clause or terms shall be interpreted as per precedence order of respective clause mentioned in the Tender, Scope of Work, SCC & GCC.

------- xx -------